HerFlow Foundation.

Full Project Management Plan — Kisii County Launch

Key data point: Kisii County has an estimated 172,344 girls aged 10–19 (2019 Kenya Population and Housing Census, KNBS). Milestone 1 of this plan narrows this to one realistic first target: a single school or ward.

# 1. Scope Management

## Project Goal

Provide sanitary products to girls in one identified school/ward in Kisii County, establishing a repeatable model for HerFlow's future expansion.

## In Scope

- Identifying and partnering with one school/ward in Kisii

- Needs assessment to determine number of girls requiring support

- Sourcing and distributing sanitary products for one distribution cycle

- Basic tracking of impact (attendance/feedback) after distribution

## Out of Scope (for now)

- County-wide distribution across all of Kisii's ~172,344 girls aged 10–19

- Long-term/ongoing monthly supply chain

- Manufacturing or producing sanitary products (HerFlow will source, not manufacture, at this stage)

# 2. Time Management

## Work Breakdown Structure & Schedule

| Phase | Task | Duration | Owner |
| --- | --- | --- | --- |
| 1. Site Selection | Identify and confirm target school/ward | Week 1–2 | Founder |
|  | Initial contact & relationship building | Week 1–2 | Founder |
| 2. Needs Assessment | Meet school contact; estimate number of girls in need | Week 2–3 | Founder + School contact |
|  | Document findings | Week 3 | Founder |
| 3. Resource Mobilization | Identify donors/suppliers; fundraise or request in-kind donations | Week 3–5 | Founder |
|  | Purchase/collect products | Week 5 | Founder |
| 4. Distribution | Deliver and distribute products at the school | Week 6 | Founder + School contact |
| 5. Follow-Up | Collect feedback; check attendance impact | Week 7–8 | Founder + School contact |
| 6. Review | Assess results; decide on next cycle/expansion | Week 9 | Founder + Mentor |

# 3. Cost Management

## Estimated Budget (Pilot Cycle — One School)

| Item | Estimated Cost (KES) | Notes |
| --- | --- | --- |
| Sanitary products (est. 100 girls x 1 pack) | ~15,000–20,000 | Adjust once real needs assessment number is known |
| Packaging/branding (optional) | ~2,000 | Simple branded bags/labels, optional for first cycle |
| Transport to Kisii site | ~3,000–5,000 | Depends on distance/frequency of visits |
| Communication (calls, data/airtime) | ~1,000 | Coordinating with school contact |
| Contingency (10%) | ~2,000 | Buffer for unexpected costs |
| Estimated Total | ~23,000–30,000 | Refine after needs assessment |

## Funding Sources to Explore

- Personal contribution / savings (seed amount to start)

- Small individual donors (friends, family, social media appeal)

- Local businesses in Kisii (salons, pharmacies, shops) for in-kind or cash donations

- Related program micro-grants, if available.

# 4. Resource Management

| Category | Details |
| --- | --- |
| Human | Founder (planning, coordination, fundraising); school contact (matron/counselor); optional volunteer for distribution day |
| Financial | Budget outlined in Section 3 |
| Material | Sanitary products, packaging, transport |
| Informational | 2019 Census data; school-provided needs data |
| Digital Tools | Google Sheets/Forms (data), Looker Studio (dashboard), GitHub (documentation), Canva/Google Slides (pitch deck) |

# 5. Quality Management

Since this is a service/impact project rather than a manufactured product, "quality" means making sure the right girls are reached, the process is dignified, and the data collected is accurate.

- Products sourced are good quality and appropriate for the age group

- Distribution is handled discreetly and respectfully (avoiding embarrassment for recipients)

- Needs assessment numbers are cross-checked with the school contact, not guessed

- Feedback is actually collected after distribution, not skipped

# 6. Communication Management

| Stakeholder | What They Need | Frequency |
| --- | --- | --- |
| School contact | Coordination on dates, numbers, logistics | Weekly during active phases |
| Members | Progress updates, blockers, questions | Weekly check-in |
| Donors | Ask, updates on how funds/products were used, thank-you | At ask + after distribution |
| Girls/recipients | Clear, respectful communication on distribution day | Distribution day only |

# 7. Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Insufficient funding | Medium | High | Start small (one school); diversify donor asks |
| School hesitation/delay | Medium | Medium | Use warm introduction via known contact |
| Inaccurate needs estimate | Low | Medium | Verify directly with school, don't rely only on county data |
| Time constraints (program + coursework) | High | Medium | Keep scope to one school only for this cycle |
| Low donor response | Medium | High | Have a personal contribution fallback for a minimal pilot batch |

# 8. Procurement Management

- Identify 2–3 suppliers/shops in Kisii or Nairobi selling sanitary products in bulk, and compare prices

- Where possible, approach manufacturers/distributors directly for a bulk/donation discount, mentioning HerFlow's mission

- Keep receipts and a simple procurement log (what was bought, from whom, at what cost) for transparency with donors and your mentor

# 9. Stakeholder Management

| Stakeholder | Interest/Influence | Engagement Approach |
| --- | --- | --- |
| Girls (recipients) | High interest, low influence over the project | Ensure dignity and respect in distribution |
| School administration | High interest, high influence (gatekeeper) | Build relationship early, communicate clearly |
| Donors | Medium interest, high influence (funding) | Regular updates, transparency, gratitude |
| Members | Medium interest, medium influence (guidance) | Regular updates and transparency |
| Community leaders | Medium interest, medium influence (trust-building) | Involve early if possible, for credibility |

# 10. Proposal Writing

A separate one-page proposal document (already drafted) is used to formally request partnership from the target school, and a data-backed pitch deck is used to approach donors. Both should stay consistent with the numbers and plan in this document.

- School proposal: requests permission + a needs assessment contact — see "HerFlow School Proposal" document

- Donor pitch deck: presents the problem (data), the ask (specific amount/products), and the plan (this document's summary) — built once the target school and real needs number are confirmed.